## Tabelle1
Calendar Week
Task | Target (h) | Actual (h) | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 13 |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 |  | 21 | 22
Project start
Problem analysis and concept developement | 12
Administration and project planning | 12
Literature | 5
Line Cutter
Investigation of options | 12
Testing of line cutters | 12
Design | 8
Hardware
Detail block diagram and core component evaluation | 5
Schematic design, bill of material (BOM) and Component ordering | 20
PCB Layout | 24
Review and production preparation | 20
Assembly and Testing | 36
Mechanical design | 12
Firmware | [9 empty] | MS1
Installation and familiarization with IDE, programmer, RTOS and setup | 8
Concept design | 5
Implementation of USB-Interface | 8
Implementation of Sensors | 20
Implementation of Telemetry | 15
Integration of modules and main application | 20
System testing | [17 empty] | MS2
Software Tests | 8
Cutting Tests | 5
Redundancy Tests | 5
Documentation | [19 empty] | MS3
Requirements Specification / Report | 76
Abstract / Poster / Elevator speech (video) | 12
Total (h): | 360 | [17 empty] | MS4 |  |  | MS5
|  |  | Target | [5 empty] | Milestone |  |  | Description
|  |  | Actual | [5 empty] | MS1 |  |  | Hardware design finished and production start
[9 empty] | MS2 |  |  | Firmware key-requirements implemented
[9 empty] | MS3 |  |  | System integration tests validated
[9 empty] | MS4 |  |  | Submission date for abstract: xxxxxxx
[9 empty] | MS5 |  |  | Submission date for thesis: 03.06.2022