## Tabelle1
Calendar Week
Task | Target (h) | Actual (h) | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 13 |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 |  | 21 | 22
Project start
Problem analysis and concept developement | 12 | 8
Administration and project planning | 12 | 8
Literature | 5 | 10
Line Cutter
Investigation of options | 12 | 12
Testing of line cutters | 12 | 10
Design | 8 | 6
Hardware
Detail block diagram and core component evaluation | 5 | 2
Schematic design, bill of material (BOM) and Component ordering | 20 | 24
PCB Layout | 24 | 20
Review and production preparation | 20 | 18
Assembly and Testing | 36 | 30
Mechanical design | 12 | 18
Firmware | [9 empty] | MS1
Installation and familiarization with IDE, programmer, RTOS and setup | 8 | 10
Concept design | 5 | 8
Implementation of USB-Interface | 8 | 4
Implementation of Sensors | 20 | 18
Implementation of Telemetry | 15 | 24
Integration of modules and main application | 20 | 36
System testing | [17 empty] | MS2
Software Tests | 8 | 10
Cutting Tests | 5 | 8
Additional Testing | 5 | 12
Documentation | [19 empty] | MS3
Requirements Specification / Report | 76 | 100
Abstract / Poster / Elevator speech (video) | 12 | 8
Total (h): | 360 | 404 | [18 empty] | MS4 | MS5
|  |  | Target | [5 empty] | Milestone |  |  | Description
|  |  | Actual | [5 empty] | MS1 |  |  | Hardware design finished and production start
[9 empty] | MS2 |  |  | Firmware key-requirements implemented
[9 empty] | MS3 |  |  | System integration tests validated
[9 empty] | MS4 |  |  | Submission date for abstract: xxxxxxx
[9 empty] | MS5 |  |  | Submission date for thesis: 04.06.2022